## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 3- Completed
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
du
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Foundations and Prerequistes for doing the project | 23rd Sep | 7th Oct | Dhruv Jindal | Leant and practiced python | Done |  | Introduction | Python and Jupyter Installation | 25th Sep: Studied Naming conventions | 26th Sep: Studied Different types of datatypes | 27th Sep: Revised naming rules and datatypes | 28th Sep: Practiced datatypes handling | 29th Sep: Studied types of flow controls | 30th Sep: Studied string operation and methods | 1st Oct: Revised string operations | 2nd Oct: Practiced flow controls and string operations | 3rd Oct: Recap of string topic and studied functions concept | 4th Oct: Revised functions | 5th Oct: Practiced string passing via functions | 6th Oct: Studied funtions and imp. of variables
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th Oct | 22nd Oct | Dhruv Jindal | Understood project architecture, implemented setup and integrated google sheets and API for the project | Done |  | Studied OOP's Concepts | Studied concept of packages | Studied NLP and text wrangling,cleaning | Studied Lemmatization and concept of spaCy library | Revised and practiced use of spaCy library | Introduction and details about project | Interaction session on project | Hands on experience to setup project using venv | Studied and installed Hugging face transformers | Project understanding interactive session | Hugging face revision | Exploration of various LLMs | Revised NLP and python libraries | Hands on of integration with google sheets
3 |  | Social Media Integration,Content Creation,Optimization | 23rd | 6th Nov | Dhruv Jindal | Studied social media api integraion and content generation techniques with practical exp. | Done |  | Hands on API Integration with twitter | Completed twitter integration and testing | Working on integration of linkedin api | Working on facebook api | Clearing doubts and interactive session | Practiced api integration | Studied mock data generation | Content creation using llm and groq api | Understanding of gsheet connector and submission of assignment | studied llm fundamentals | revised llm models | Tried variations of assignement submitted | Studied generation of version of content | Hands on with the template
4 |  | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | Dhruv Jindal | Studied Sentiment Analysis, Slack Integration and deployment on streamlit | Done |  | Studied concept of API | Studied concept of API | Revised API | Hands on Assignment | Interactive session | Studied content optimization | Studied Sentiment Analysis | Studied slack integration | Studied A/B testing | Revised A/B testing | Revised content optimization | Understood about Project Workflow | Discussion about Project Presentation | Mock presentation
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7